## Summary
Signed Sales Order / Pending Shop Drawings - deal-by-deal check
Source: monday.com Opportunities board, group "Signed Sales Order/Pending Shop Drawings", pulled 10/2/26. Cross-checked to the Project Managers board and the 2026 customer deposit tabs.
Classification | # Deals | Project Total | Panda #
Valid backlog
Check - 2025 win, no deposit, not on PM board
Remove - already produced / shipped
Remove - canceled on PM board
Won in October (after 10/1 snapshot)
Total in group today
As shown on dashboard (10/1 snapshot): all deals won before 10/1
Dashboard figure (hardcoded) | 140 | 9700000 |  | Typed into the dashboard page; not recalculated
Corrected backlog: valid + to check
Corrected backlog: valid only
Notes
14 deals have no Project Total entered, so their value is missing from every dollar figure.
"Deposit on 2026 tab" only checks the Jan-Sep 2026 customer deposit tabs; a deposit collected in 2025 will show No.
Remove rows: the PM board already shows these jobs shipped, closed out or canceled, so they are not waiting on shop drawings. Move them out of this group in monday.
Check rows: won in 2025, no 2026 deposit and no PM board job. Probably dead or never started; confirm with the RSM.

## Deals
RSM | Deal | Project / Company | Q# | Stage | Deal Won | Won Date | Project Total | Panda # | Shop Drawings? | Drawings Signed? | PM Board Group | Deposit on 2026 tab | Classification | Opp Last Updated | monday link
Bill Davenport | Daniel Moran | Moran Residence | 90891 / 2092 | Signed SO/Pending Drawings | Yes | 2026-07-29 | 9757 | 5217 | No | No | Not on PM board | No | Valid backlog | 2026-08-06 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11989151816
Bill Davenport | Kenneth VanBuskirk | Detroit Pistons Locker Room | 92529 | Signed SO/Pending Drawings | Yes | 2026-09-10 |  |  | No | No | Not on PM board | No | Valid backlog | 2026-09-25 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12970532244
Derrick McCall | J Shuman Door Installation | Hospitality Building | 86579 | Signed SO/Pending Drawings | Yes | 2026-06-15 | 153173 | 135977.87 | Yes | No | Sent to Engineering | Yes | Valid backlog | 2026-07-09 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/9645512025
Derrick McCall | Best Contracting | UCSB San Benito Housing | 87022 | Signed SO/Pending Drawings | Yes | 2025-11-04 | 121645 | 107495.35 | Yes | No | Sent to Engineering | Yes | Valid backlog | 2026-04-08 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/18346441407
Derrick McCall | Pacific Glazing Contractors | Mission Bay South 4E Phase 2 | 89502 | Proposal Sent to Client | Yes | 2026-04-29 | 107644 | 92836.96 | No | No | Pending Deposit in Invoicing | No | Valid backlog | 2026-04-29 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11342933243
Derrick McCall | Classic Glass | Hotel Mohi | 88845 | Signed SO/Pending Drawings | Yes | 2026-03-20 | 103637 | 90249.35 | Yes | No | Sent to Engineering | Yes | Valid backlog | 2026-04-16 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11556409277
Derrick McCall | Progress Glass | Marin Art & Garden Center | 91229 / 2493 | Signed SO/Pending Drawings | Yes | 2026-09-16 | 98131.6 | 82015.63 | Yes | No | Not on PM board | Yes | Valid backlog | 2026-09-24 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12197775710
Derrick McCall | Capitol Glass Company | The Eliza | 84966 | Signed SO/Pending Drawings | Yes | 2025-09-24 | 79208 | 67627.5 | Yes | No | Sent to Engineering | Yes | Valid backlog | 2026-04-08 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/8917925091
Derrick McCall | Sunset Glazing | 6th & Palm | 84176/4141 | Signed SO/Pending Drawings | Yes | 2026-08-11 | 78196.39 | 67355.35 | No | No | Not on PM board | Yes | Valid backlog | 2026-08-27 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/8627892187
Derrick McCall | Lucky's Glass | Meditation | 86347 / 4593 | Signed SO/Pending Drawings | Yes | 2026-08-31 | 65888.32 | 57344.82 | No | No | Not on PM board | No | Valid backlog | 2026-08-31 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/9534718348
Derrick McCall | Giroux Glass | Sparks Training Facility | 89539 | Signed SO/Pending Drawings | Yes | 2026-05-20 | 65212 | 5535.75 | Yes | No | Pending Deposit in Invoicing | Yes | Valid backlog | 2026-08-10 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11358077145
Derrick McCall | Walters & Wolf | UCB Bancroft | 87035 | Signed SO/Pending Drawings | Yes | 2026-06-02 | 56357 | 48347.41 | Yes | No | Sent to Engineering | Yes | Valid backlog | 2026-06-15 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/9882140955
Derrick McCall | Elite Glaziers | LA Basketball | 90706 | Signed SO/Pending Drawings | Yes | 2026-05-06 | 52480 | 45833.22 | Yes | No | Sent to Engineering | Yes | Valid backlog | 2026-06-17 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11801141862
Derrick McCall | Platinum Glass | JP Morgan Chase 7th | 89431 | Signed SO/Pending Drawings | Yes | 2026-03-27 | 48064 | 42001.39 | No | No | Pending Deposit in Invoicing | No | Valid backlog | 2026-04-08 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11295209764
Derrick McCall | Platinum Glass | JP Morgan Chase 8th | 89430 | Signed SO/Pending Drawings | Yes | 2026-03-27 | 48064 | 42001.39 | No | No | Pending Deposit in Invoicing | No | Valid backlog | 2026-04-08 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11295213702
Derrick McCall | AAC Glass Inc | PUSD Folding Door | 88164 | Signed SO/Pending Drawings | Yes | 2026-06-05 | 44565 | 37957.25 | No | No | Pending Deposit in Invoicing | Yes | Valid backlog | 2026-06-05 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12202842142
Derrick McCall | Capital Glass Company | 34th and San Pablo | 86644 | Signed SO/Pending Drawings | Yes | 2025-11-14 | 34422.21 | 26331.1 | Yes | No | Sent to Engineering | Yes | Valid backlog | 2026-08-25 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/10567219045
Derrick McCall | Aragon Construction | 216B - Replacement | 92404 / 4620 | Signed SO/Pending Drawings | Yes | 2026-08-31 | 33776.18 | 27629.31 | No | No | Not on PM board | Yes | Valid backlog | 2026-09-16 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12906740141
Derrick McCall | Liberty Glass & Metal, Inc | Irvine | 89690/2533 | Signed SO/Pending Drawings | Yes | 2026-08-05 | 27103.24 | 22286.7 | No | No | Not on PM board | Yes | Valid backlog | 2026-08-12 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11437498416
Derrick McCall | Lincoln Glass & Mirror | Concord | 89522 | Signed SO/Pending Drawings | Yes | 2026-07-02 | 16399 | 12195.45 | No | No | Not on PM board | Yes | Valid backlog | 2026-07-13 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11352915067
Derrick McCall | Elevate Home | 4005 Alonzo Ave | 91449/2830 | Signed SO/Pending Drawings | Yes | 2026-07-20 | 14448.17 | 11248.39 | Yes | No | Not on PM board | Yes | Valid backlog | 2026-09-11 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12340289913
Derrick McCall | Maryl Construction | 91108 Hapuna Villa Window | 91108 / 2343 | Signed SO/Pending Drawings | No | 2026-06-19 | 10033.21 | 9449.26 | No | No | Pending Deposit in Invoicing | Yes | Valid backlog | 2026-08-10 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12321628016
Derrick McCall | JV Glass | Lululemon |  | Proposal Sent to Client | Yes | 2026-04-29 |  |  | No | No | Not on PM board | No | Valid backlog | 2026-04-29 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11756438433
Derrick McCall | Ian Russell |  |  | Signed SO/Pending Drawings | Yes | 2026-04-29 |  |  | No | No | Not on PM board | No | Valid backlog | 2026-04-29 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11775899142
Derrick McCall | Lighthouse Windows, Inc | Warm Springs III - Lot 10 | 91004 / 2209 | Signed SO/Pending Drawings | Yes | 2026-05-26 |  |  | No | No | Pending Deposit in Invoicing | Yes | Valid backlog | 2026-05-26 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12107680812
Derrick McCall | Signature Glass & Windows, Inc. | 3001 ECR | 87059 | Signed SO/Pending Drawings | Yes | 2026-06-05 |  |  | Yes | No | Sent to Engineering | Yes | Valid backlog | 2026-06-29 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12202875911
Efrain Zarate | Dynamic Glass | Antero Resources | 85504 | Signed SO/Pending Drawings | Yes | 2026-02-09 | 302136 | 260821.74 | Yes | No | Sent to Engineering | Yes | Valid backlog | 2026-08-17 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/9322025496
Efrain Zarate | Roseman University of Health Sciences, A Non-Profit Corporation | Roseman University | 88519/2436 | Signed SO/Pending Drawings | Yes | 2026-09-10 | 171300.72 | 157156.62 | No | No | Not on PM board | No | Valid backlog | 2026-09-10 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/10746878829
Efrain Zarate | The Window Store | Black Spur Estate | 85860 | Signed SO/Pending Drawings | Yes | 2025-06-09 | 144167 | 125877.52 | Yes | No | Sent to Engineering | Yes | Valid backlog | 2026-04-08 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/8775248357
Efrain Zarate | Walters & Wolf | HRHC Podium | 87948/4063 | Signed SO/Pending Drawings | Yes | 2026-08-11 | 132268.93 | 119456 | No | No | Not on PM board | Yes | Valid backlog | 2026-09-16 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12741345459
Efrain Zarate | Sighlines | Blue Martini | 87599 | Signed SO/Pending Drawings | Yes | 2025-11-04 | 108261 | 96526.01 | Yes | No | Pending Deposit in Invoicing | Yes | Valid backlog | 2026-08-17 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/18346471113
Efrain Zarate | Turkel Design | Robbins | 89724/2803 | Signed SO/Pending Drawings | Yes | 2026-09-04 | 105977.5 | 83454.5 | Yes | No | Not on PM board | Yes | Valid backlog | 2026-09-29 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11884841301
Efrain Zarate | Turkel Design | GAL Residence | 87450 | Signed SO/Pending Drawings | Yes | 2026-02-13 | 59540 | 46827.47 | Yes | No | Sent to Engineering | Yes | Valid backlog | 2026-06-10 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/18025593941
Efrain Zarate | Architectural Windows & Doors | NM Remodel | 91603 | Signed SO/Pending Drawings | Yes | 2026-08-14 | 58451 | 47950.47 | Yes | No | Not on PM board | Yes | Valid backlog | 2026-09-23 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12426049763
Efrain Zarate | Glass House | Red Arrow | 88672 | Signed SO/Pending Drawings | Yes | 2026-05-01 | 47238 | 42892.07 | No | No | Sent to Engineering | No | Valid backlog | 2026-08-17 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11076421267
Efrain Zarate | Skyline Glass | Candela's Apartments | 86208 | Signed SO/Pending Drawings | Yes | 2026-04-24 | 45573 | 36339.28 | Yes | No | Sent to Engineering | Yes | Valid backlog | 2026-05-15 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11842196498
Efrain Zarate | C Thru Glass | Mt. Charleston Lodge | 89607 | Signed SO/Pending Drawings | Yes | 2026-04-08 | 38670 | 34479.18 | Yes | No | Sent to Engineering | Yes | Valid backlog | 2026-08-17 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11464599738
Efrain Zarate | BMG Door & Glass | Halise Diamond | 89197 | Signed SO/Pending Drawings | No |  | 38046.13 | 33122.14 | Yes | No | Not on PM board | Yes | Valid backlog | 2026-08-17 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11778239085
Efrain Zarate | Ken Caryl Glass Inc | McDonald Audi | 91176/2447 | Signed SO/Pending Drawings | Yes | 2026-09-04 | 35384.86 | 29192.58 | Yes | No | Not on PM board | Yes | Valid backlog | 2026-09-21 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12181024331
Efrain Zarate | Tridel Construction | Players Canyon - Doors | 84246 | Signed SO/Pending Drawings | Yes | 2025-11-17 | 34230 | 30940.12 | Yes | No | Sent to Engineering | Yes | Valid backlog | 2026-04-08 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/8646895020
Efrain Zarate | 8 G Solutions | Marina Square | 83756/2591 | Signed SO/Pending Drawings | Yes | 2026-07-23 | 29958.12 | 23292.77 | Yes | No | Not on PM board | Yes | Valid backlog | 2026-08-17 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11885010447
Efrain Zarate | Amber Martinez | Martinez Pivot | 92314/4228 | Signed SO/Pending Drawings | Yes | 2026-08-18 | 29037.48 | 25079.7 | No | No | Not on PM board | Yes | Valid backlog | 2026-08-21 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12777585608
Efrain Zarate | Mesa Properties | 2435 Legacy Dr | 85687 | Signed SO/Pending Drawings | Yes | 2026-07-30 | 26587 | 22382 | Yes | No | Not on PM board | Yes | Valid backlog | 2026-08-06 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12582634150
Efrain Zarate | American Eagle Glass | AAA Blue Diamond | 91452/ 2847 | Signed SO/Pending Drawings | Yes | 2026-07-14 | 17267.58 | 15238.87 | No | No | Not on PM board | Yes | Valid backlog | 2026-08-17 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12342014464
Efrain Zarate | Grand View Glass- Chris Medina | LMAC Operable Glass Wall | 89541 | Signed SO/Pending Drawings | Yes | 2026-06-03 | 17182 | 13094.38 | No | No | Pending Deposit in Invoicing | Yes | Valid backlog | 2026-06-30 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11362449632
Efrain Zarate | Elham Taherian | 2180 Havensight Add On 2 | 91377/2792 | Signed SO/Pending Drawings | Yes | 2026-08-18 | 14958.17 | 13447.08 | Yes | No | Not on PM board | Yes | Valid backlog | 2026-09-15 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12322563037
Efrain Zarate | Steven Thomas | 5162 Rock Daisy | 83357 | Signed SO/Pending Drawings | Yes | 2025-03-13 | 10055 | 9087.42 | No | No | Pending Deposit in Invoicing | No | Valid backlog | 2026-08-17 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/8214177954
Efrain Zarate | Gary Kortz | Gary Kortz | 82669 | Signed SO/Pending Drawings | Yes | 2025-03-10 | 7504 | 4853.63 | No | No | Pending Deposit in Invoicing | No | Valid backlog | 2026-08-17 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/8117297810
Efrain Zarate | Charles Benbow | Benbow Add On | 91255/2522 | Signed SO/Pending Drawings | Yes | 2026-09-24 |  |  | No | No | Not on PM board | No | Valid backlog | 2026-09-24 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12220521872
Sean Torre | Juan Molina | Kanani Residence | 86089 | Signed SO/Pending Drawings | Yes | 2025-10-17 | 819158 | 722725.41 | Yes | No | Sent to Engineering | Yes | Valid backlog | 2026-06-10 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/9422515889
Sean Torre | Eclipse Residence | Eclipse Reidence | 86157 | Signed SO/Pending Drawings | Yes | 2026-02-12 | 510051 | 448501.29 | Yes | No | Sent to Engineering | Yes | Valid backlog | 2026-06-09 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11267307021
Sean Torre | Shuman Doors | 1420 University ave | 91748 / 3556 | Signed SO/Pending Drawings | Yes | 2026-08-20 | 131609.71 | 121662.95 | No | No | Not on PM board | Yes | Valid backlog | 2026-08-20 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12601509176
Sean Torre | Todd Nelson | DFW Terminal C | 86704 | Signed SO/Pending Drawings | Yes | 2026-02-05 | 113687 | 98199.36 | Yes | No | Sent to Engineering | Yes | Valid backlog | 2026-04-08 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/9709418646
Sean Torre | Shuman Doors | 1901 Gilman Ranch Rd | 92172/3956 | Signed SO/Pending Drawings | Yes | 2026-09-02 | 79631.92 | 65873.79 | Yes | No | Not on PM board | Yes | Valid backlog | 2026-09-30 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12725867439
Sean Torre | Tier One Custom Windows | Mt. Bonnell | 89969 | Signed SO/Pending Drawings | Yes | 2026-09-21 | 74601.67 | 95068.62 | No | No | Not on PM board | No | Valid backlog | 2026-09-21 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12337378993
Sean Torre | Doganis Residence | Doganis Residence | 87185 | Signed SO/Pending Drawings | Yes | 2025-11-19 | 63029 | 55943.71 | Yes | No | Sent to Engineering | Yes | Valid backlog | 2026-04-27 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/10600540558
Sean Torre | Builders Direct Supply | Lift & Slide Options | 92187 / 4496 | Signed SO/Pending Drawings | Yes | 2026-09-30 | 61400.88 | 50618.24 | No | No | Not on PM board | No | Valid backlog | 2026-09-30 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12863634399
Sean Torre | Alba Jubani | Illy at Cosmo | 85778 | Signed SO/Pending Drawings | Yes | 2025-05-28 | 59707 | 52997.5 | No | No | Pending Deposit in Invoicing | No | Valid backlog | 2026-04-08 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/9253084020
Sean Torre | Tier One Custom Windows | 21830 Briarcliff Dr |  | Signed SO/Pending Drawings | Yes | 2026-09-03 | 37994.19 | 32875.42 | No | No | Not on PM board | No | Valid backlog | 2026-09-03 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12969004516
Sean Torre | Don's Mobile Glass | Mikha, Linda | 91567 | Signed SO/Pending Drawings | Yes | 2026-08-10 | 31679.47 | 40178.62 | No | No | Not on PM board | No | Valid backlog | 2026-08-20 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12763172501
Sean Torre | Integrated door and windows | Patel Entry Door | 92437 / 4086 | Signed SO/Pending Drawings | Yes | 2026-09-14 | 25916.61 | 21717.08 | No | No | Not on PM board | No | Valid backlog | 2026-09-14 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12750039925
Sean Torre | Builders Direct Supply | Johnson Entry Door | 91561 | Signed SO/Pending Drawings | Yes | 2026-08-18 | 20578.87 | 18439.33 | No | No | Not on PM board | Yes | Valid backlog | 2026-08-21 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12833812260
Sean Torre | The Martin | The Martin | 88971 | Signed SO/Pending Drawings | No |  | 18595.53 | 14186.97 | No | No | Not on PM board | Yes | Valid backlog | 2026-07-14 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12361303256
Sean Torre | Lee Glass & Window | Eisenhower Elementary School Expansion | 90333 | Signed SO/Pending Drawings | Yes | 2026-07-14 | 17299.81 | 12403.49 | No | No | Not on PM board | Yes | Valid backlog | 2026-07-28 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11748235978
Sean Torre | Rudy Gomez | 415 College Main | 87805 | Signed SO/Pending Drawings | Yes | 2025-12-16 | 14582 | 10095.03 | Yes | No | Sent to Engineering | Yes | Valid backlog | 2026-04-08 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/18194141866
Sean Torre | Shuman Doors | 1285 W Edmundson Ave | 91739 / 4578 | Signed SO/Pending Drawings | Yes | 2026-09-02 | 10347.73 | 11985.98 | No | No | Not on PM board | Yes | Valid backlog | 2026-09-16 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12957821074
Sean Torre | Shuman Doors | Arnaud - Add on | 91978 | Signed SO/Pending Drawings | Yes | 2026-08-20 | 1093.38 | 865.49 | No | No | Not on PM board | No | Valid backlog | 2026-08-20 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12858595683
Sean Torre | Nandini Saraiya | Nandini Saraiya | 89168 | Signed SO/Pending Drawings | Yes | 2026-04-22 |  |  | No | No | Sent to Engineering | Yes | Valid backlog | 2026-04-24 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11823251514
Stefan Monetta | Harmon - Maryland | 725 W 12th St | 87189 | Signed SO/Pending Drawings | Yes | 2026-08-25 | 443655.7 | 400693.3 | Yes | No | Not on PM board | Yes | Valid backlog | 2026-09-09 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/9964657740
Stefan Monetta | Ryan Snabes | Ann Arbor Thurston | 84161 | Signed SO/Pending Drawings | Yes | 2025-10-01 | 353373 | 315296.32 | Yes | No | Sent to Engineering | Yes | Valid backlog | 2026-06-10 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/9127892120
Stefan Monetta | Trendex Corp | 1826 S Bayshore Lane | 88397 | Signed SO/Pending Drawings | Yes | 2026-02-05 | 240667 | 211099 | Yes | No | Sent to Engineering | Yes | Valid backlog | 2026-04-08 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11201081350
Stefan Monetta | Dan and Molly Dirscherl | Dirscherl Cabana | 85777 | Signed SO/Pending Drawings | Yes | 2026-03-02 | 177689 | 160979.9 | Yes | No | Sent to Engineering | Yes | Valid backlog | 2026-07-07 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11403344967
Stefan Monetta | David Ostrander (Boat House) | Ostrander Boat House | 89178 | Signed SO/Pending Drawings | Yes | 2026-02-23 | 72444 | 62813.14 | No | No | Pending Deposit in Invoicing | No | Valid backlog | 2026-06-10 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11342786430
Stefan Monetta | Glass & Metals | 2100 Crystal | 88012 | Signed SO/Pending Drawings | Yes | 2026-05-12 | 50922 | 42889.34 | Yes | No | Pending Deposit in Invoicing | Yes | Valid backlog | 2026-06-09 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/18319424513
Stefan Monetta | Ajay Glass Co. | Sayers Resident | 92799 | Signed SO/Pending Drawings | Yes | 2026-09-10 | 50511.51 | 39261.82 | No | No | Not on PM board | Yes | Valid backlog | 2026-09-24 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/13019393192
Stefan Monetta | S. Albert Glass Co. | Womble Bond Dickinson | 91363 | Signed SO/Pending Drawings | Yes | 2026-09-25 | 46472.81 | 35971.62 | No | No | Not on PM board | No | Valid backlog | 2026-09-25 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/13137557866
Stefan Monetta | Advanced Window, Inc | 1990 K Street | 87616 | Signed SO/Pending Drawings | Yes | 2026-02-04 | 44961 | 37463.65 | Yes | No | Sent to Engineering | Yes | Valid backlog | 2026-06-09 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/18098472722
Stefan Monetta | Keith Starkey | Starkey Residence | 78503 | Signed SO/Pending Drawings | Yes | 2025-06-16 | 31629 | 24003.52 | Yes | No | Sent to Engineering | Yes | Valid backlog | 2026-06-09 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/9366873756
Stefan Monetta | Ajay Glass Co. | Billiter South | 90513 | Signed SO/Pending Drawings | Yes | 2026-09-17 | 29671.25 | 21959.54 | No | No | Not on PM board | Yes | Valid backlog | 2026-09-24 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11809350053
Stefan Monetta | Scott Hawkins | Hawkins Residence | 91020 | Signed SO/Pending Drawings | Yes | 2026-07-07 | 25575.9 | 19996.9 | No | No | Pending Deposit in Invoicing | No | Valid backlog | 2026-07-07 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12079669060
Stefan Monetta | Klein Dickert Milwakee Inc. | Artalia Senior Living | 90043 | Signed SO/Pending Drawings | Yes | 2026-08-19 | 21965.81 | 16643.42 | No | No | Not on PM board | Yes | Valid backlog | 2026-08-31 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12807318540
Stefan Monetta | Matthew Daniel | Daniel Res | 85396 | Signed SO/Pending Drawings | Yes | 2026-04-23 | 19584 | 13851.41 | No | No | Sent to Engineering | Yes | Valid backlog | 2026-06-09 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11834734434
Stefan Monetta | Matthew Daniel | Daniel Res | 85396 | Signed SO/Pending Drawings | Yes | 2026-04-23 | 19584 | 13851.41 | No | No | Sent to Engineering | Yes | Valid backlog | 2026-06-09 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11834726305
Stefan Monetta | Matthew Daniel | Daniel Res | 85396 | Signed SO/Pending Drawings | Yes | 2026-04-23 | 19584 | 13851.41 | No | No | Sent to Engineering | Yes | Valid backlog | 2026-06-09 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11834725746
Stefan Monetta | Matthew Daniel | Daniel Res | 85396 | Signed SO/Pending Drawings | Yes | 2026-05-25 | 19584 | 13851.41 | No | No | Sent to Engineering | Yes | Valid backlog | 2026-06-09 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/9031631347
Stefan Monetta | Steve Bell | Worth SD P27 | 80858 | Signed SO/Pending Drawings | Yes | 2025-01-14 | 13686 | 8879.2 | No | No | Sent to Engineering | Yes | Valid backlog | 2026-06-01 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/8241706192
Stefan Monetta | Clerestory LLC | Malireddy Pivot Door | 89254 | Signed SO/Pending Drawings | Yes | 2026-04-23 |  |  | Yes | No | Sent to Engineering | Yes | Valid backlog | 2026-06-10 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11833868966
Stefan Monetta | Reflection Window + Wall | Bally's Chicago Casino | 90293 | Signed SO/Pending Drawings | Yes | 2026-05-12 |  |  | Yes | No | Sent to Engineering | Yes | Valid backlog | 2026-06-02 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11993669702
Trevor Benthagen | Jairo Cadena | Cadena Residence Alternate | 90541 / 2340 | Signed SO/Pending Drawings | Yes | 2026-06-04 | 245378.14 | 211482.19 | No | No | Pending Deposit in Invoicing | No | Valid backlog | 2026-08-17 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11820382060
Trevor Benthagen | Craig Campbell, Sierra Pacific Windows | Silence Residence | 92285 / 3906 | Signed SO/Pending Drawings | Yes | 2026-09-28 | 241158.25 | 212062.61 | Yes | Yes | Not on PM board | Yes | Valid backlog | 2026-09-28 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12708565152
Trevor Benthagen | Steve Hernandez, Sierra Pacific Windows | 4545 Tremont Doors | 91699 / 3711 | Signed SO/Pending Drawings | Yes | 2026-09-22 | 137544.7 | 123986.79 | No | No | Not on PM board | Yes | Valid backlog | 2026-09-22 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11762749119
Trevor Benthagen | Mike Haskell, Sierra Pacific Windows | 1850 White Oak Dr. | 92463 / 4543 | Signed SO/Pending Drawings | Yes | 2026-09-24 | 136558.27 | 120088.32 | No | No | Not on PM board | Yes | Valid backlog | 2026-09-24 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12835003618
Trevor Benthagen | Kason Sullivan | Jeperson Remodel 4 PHASE 1 | 92246 / 3897 | Signed SO/Pending Drawings | Yes | 2026-08-04 | 38876.84 | 32552.25 | No | No | Not on PM board | Yes | Valid backlog | 2026-09-22 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12707559837
Trevor Benthagen | Mike Haskell, Sierra Pacific Windows | 1850 White Oak Dr. Corner Unit (TS.XO) | 95208 | Signed SO/Pending Drawings | Yes | 2026-09-24 | 29967.68 | 26930.17 | No | Yes | Pending Deposit in Invoicing | Yes | Valid backlog | 2026-09-24 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/13051621712
Trevor Benthagen | William Clark | Clark Slider | 89839 | Signed SO/Pending Drawings | Yes | 2026-03-31 | 16055 | 12675.54 | No | No | Pending Deposit in Invoicing | No | Valid backlog | 2026-08-17 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11487788991
Trevor Benthagen | Peak Glass, John Henry Schmitt | 555 Scott Lane | 90778 / 2875 | Signed SO/Pending Drawings | Yes | 2026-07-23 | 15475.51 | 12793.24 | Yes | No | Not on PM board | Yes | Valid backlog | 2026-08-18 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12615050539
Trevor Benthagen | Vivien Withington, Sierra Pacific Windows | Fir Mountain Garage Sauna | 92755 / 4765 | Signed SO/Pending Drawings | Yes | 2026-09-21 | 3664.17 | 2074.46 | No | No | Not on PM board | Yes | Valid backlog | 2026-09-21 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12936978862
Tyler Clark | AS Designs | 39 Melanie Lane | 92233 | Signed SO/Pending Drawings | Yes | 2026-08-24 | 437328 | 391917.86 | Yes | No | Not on PM board | Yes | Valid backlog | 2026-09-30 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12237137198
Tyler Clark | Rick - Scanlon Construction | 736 El Medio | 95111 | Signed SO/Pending Drawings | Yes | 2026-09-23 | 333030.84 | 290484.27 | No | No | Not on PM board | Yes | Valid backlog | 2026-09-23 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/13120788104
Tyler Clark | Tim Lancaster | Lake Residence | 91787 | Signed SO/Pending Drawings | Yes | 2026-07-24 | 58638.14 | 51197.75 | Yes | No | Not on PM board | Yes | Valid backlog | 2026-09-17 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12622172998
Tyler Clark | Donatello Bonasera Development, LLC | Double Pivot | 95324 | Signed SO/Pending Drawings | Yes | 2026-09-18 | 50980.82 | 44367.09 | No | No | Not on PM board | No | Valid backlog | 2026-09-18 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12945767561
Tyler Clark | Robert Capp | Capp Folding Door | 90393 / 1485 | Signed SO/Pending Drawings | Yes | 2026-09-22 | 14369.99 | 12073 | No | No | Not on PM board | No | Valid backlog | 2026-09-22 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12111442915
Tyler Clark | Jeremy D. Whalon | Whaleon Residence | 86092 | Signed SO/Pending Drawings | Yes | 2026-04-06 |  | 16225 | No | No | Sent to Engineering | Yes | Valid backlog | 2026-06-19 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11682599918
Tyler Clark | David Roberson | SDCCD Student Housing | 95062 | Signed SO/Pending Drawings | Yes | 2026-09-10 |  |  | No | No | Not on PM board | Yes | Valid backlog | 2026-09-16 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12886996989
| Navarex Group LLC | Showroom Pivot Door | 84876 | Signed SO/Pending Drawings | Yes | 2025-04-24 | 10000 | 10000 | No | No | Not on PM board | No | Check - 2025 win, no deposit, not on PM board | 2026-07-07 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/9001127395
Efrain Zarate | Hall Aluminum Products | HUB Boulder | 85127 | Signed SO/Pending Drawings | Yes | 2025-04-22 |  |  | Yes | No | Not on PM board | No | Check - 2025 win, no deposit, not on PM board | 2026-08-17 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/8972612230
Joseph Tydingco | Test Client |  |  | Signed SO/Pending Drawings | Yes | 2025-08-12 |  |  | No | No | Not on PM board | No | Check - 2025 win, no deposit, not on PM board | 2026-04-08 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/9798707027
Stefan Monetta | Gallin | 640 5th Ave | 85732 | Signed SO/Pending Drawings | Yes | 2025-10-09 | 42683 | 35379.46 | No | No | Not on PM board | No | Check - 2025 win, no deposit, not on PM board | 2026-06-09 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/18150722684
Stefan Monetta | Wally Abdal | Abdal, Walid Entry Steel | 80527 | Signed SO/Pending Drawings | Yes | 2025-01-14 | 16594 | 11563 | No | No | Not on PM board | No | Check - 2025 win, no deposit, not on PM board | 2026-06-01 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/8241706257
Avi Shoshan | George Yousefi | Windows & Sliders | 87296 | Signed SO/Pending Drawings | Yes | 2026-02-24 | 67362 | 66365.73 | Yes | Yes | Completed - Closed Out | Yes | Remove - already produced / shipped | 2026-04-08 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11357849839
Avi Shoshan | George Yousefi | George_Additional Fixed Window | 89773 | Signed SO/Pending Drawings | Yes | 2026-03-11 |  |  | No | No | Completed - Closed Out | Yes | Remove - already produced / shipped | 2026-04-08 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11481725778
Derrick McCall | Boyette Door | Kirkwood | 79181 | Signed Shop Drawings | Yes | 2025-06-10 | 291600 | 79181 | No | Yes | Completed - Closed Out | No | Remove - already produced / shipped | 2026-04-08 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/8969004348
Derrick McCall | Lunstrum Windows | Park Summit | 79059 | Signed SO/Pending Drawings | Yes | 2026-03-10 | 174843 | 151337.69 | No | No | Completed - Closed Out | Yes | Remove - already produced / shipped | 2026-04-08 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11472764149
Derrick McCall | USGA Inc | Middlefield Junction | 78363 | Signed Shop Drawings | Yes | 2025-06-10 | 65716 | 56198.29 | No | Yes | Completed - Closed Out | No | Remove - already produced / shipped | 2026-04-08 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/8845235836
Derrick McCall | Boyett Construction Inc | Russell | 90450 | Signed SO/Pending Drawings | Yes | 2026-04-22 | 15398.29 | 11611.1 | Yes | No | Completed - Closed Out | Yes | Remove - already produced / shipped | 2026-05-20 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11817087034
Sean Torre | Builder's Direct Supply | Larroque Door | 88582 | Signed Shop Drawings | Yes | 2026-03-24 | 8179 | 6069.24 | Yes | Yes | Completed - Closed Out | Yes | Remove - already produced / shipped | 2026-06-09 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/10793866324
Sean Torre | MP Services | 37 Pained feather Way - 77's / track | 87704 | Signed SO/Pending Drawings | Yes | 2025-11-04 | 3952 | 3802 | No | No | Completed - Closed Out | Yes | Remove - already produced / shipped | 2026-04-08 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/18347522062
Stefan Monetta | Andy Rowland | Rowland Residence | 79182 | Signed SO/Pending Drawings | Yes | 2025-01-14 | 97138 | 84.026 | No | No | Completed - Closed Out | No | Remove - already produced / shipped | 2026-06-01 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/8241705860
Stefan Monetta | Powell Residence | Rob DelBiondo | 75339 | Signed SO/Pending Drawings | Yes | 2025-01-14 | 93965 | 80442.9 | No | No | Completed - Closed Out | No | Remove - already produced / shipped | 2026-06-12 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/8241706078
Stefan Monetta | Starling | Rafael Robles | 80181 | Signed SO/Pending Drawings | Yes | 2025-01-14 | 45633 | 35209.42 | No | No | Completed - Closed Out | No | Remove - already produced / shipped | 2026-06-01 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/8241706037
Stefan Monetta | Edgar Orta | Fiesta Mariachi Patio | 80785 | Signed SO/Pending Drawings | Yes | 2025-01-14 | 45076 | 35739.42 | No | No | Completed - Closed Out | No | Remove - already produced / shipped | 2026-06-01 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/8241706170
Stefan Monetta | Michelle Wiseman | Wiseman - Residence | 81626 | Signed SO/Pending Drawings | Yes | 2025-01-14 | 43513 | 35359.31 | No | No | Completed - Closed Out | No | Remove - already produced / shipped | 2026-06-10 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/8241706111
Stefan Monetta | Dale Harris | Lot 22 | 81666 | Signed SO/Pending Drawings | Yes | 2025-01-14 | 43369 | 38773.77 | No | No | Completed - Closed Out | No | Remove - already produced / shipped | 2026-06-01 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/8241706384
Stefan Monetta | Tyler Epstein | Oak View | 79275 | Signed SO/Pending Drawings | Yes | 2025-01-14 | 31322 | 24573.12 | No | No | Completed - Closed Out | No | Remove - already produced / shipped | 2026-06-10 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/8241706137
Stefan Monetta | Ashley Dearyan | Enclave Lot 3 | 80155 | Signed SO/Pending Drawings | Yes | 2025-01-14 | 30921 | 27741 | Yes | No | Completed - Closed Out | No | Remove - already produced / shipped | 2026-06-01 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/8241706319
Stefan Monetta | Chris Rogalny | Metro 19 Slider | 81773 | Signed SO/Pending Drawings | Yes | 2025-01-14 | 27160 | 20967.98 | No | No | Completed - Closed Out | No | Remove - already produced / shipped | 2026-06-01 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/8241706349
Stefan Monetta | Ben Biery | Silo Radius | 87104 | Signed Shop Drawings | Yes | 2026-02-10 | 23224 | 17047.26 | Yes | Yes | Completed - Closed Out | Yes | Remove - already produced / shipped | 2026-06-09 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/9905680456
Stefan Monetta | Dave Hellyer | J.Jordan Homes Project | 80893 | Signed SO/Pending Drawings | Yes | 2025-01-14 | 21082 | 15055.61 | No | No | Completed - Closed Out | No | Remove - already produced / shipped | 2026-07-15 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/8241705968
Stefan Monetta | Babl Company Inc. | Weber | 83973 | Signed SO/Pending Drawings | Yes | 2025-10-23 | 20164 | 15666.56 | Yes | Yes | Completed - Closed Out | No | Remove - already produced / shipped | 2026-06-10 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/9051520626
Stefan Monetta | Tom Benson | Tom Benson | 82877 | Signed SO/Pending Drawings | Yes | 2025-01-14 | 12900 | 7884.73 | Yes | No | Completed - Closed Out | No | Remove - already produced / shipped | 2026-06-09 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/8238707925
Stefan Monetta | Lou Frances Maschio | Patio Folding | 76426 | Signed SO/Pending Drawings | Yes | 2025-01-14 | 12732 | 8644.44 | No | No | Completed - Closed Out | No | Remove - already produced / shipped | 2026-06-01 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/8241705922
Stefan Monetta | Orsello Family Project | Crecia Orsello | 79942 | Signed SO/Pending Drawings | Yes | 2025-01-14 | 10764 | 6066.65 | No | No | Completed - Closed Out | No | Remove - already produced / shipped | 2026-06-01 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/8241705997
Stefan Monetta | Window Classics | 9712 Kilgore Road | 84816 | Signed SO/Pending Drawings | Yes | 2025-05-13 | 52385 | 40918 | Yes | No | Canceled Jobs | Yes | Remove - canceled on PM board | 2026-04-08 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/9130940265
Stefan Monetta | Mister Window Holding Corp. | Camp | 78496 | Signed SO/Pending Drawings | Yes | 2025-01-24 | 43678 | 31848 | Yes | No | Canceled Jobs | No | Remove - canceled on PM board | 2026-04-08 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/8313362156
Stefan Monetta | Action Store Fronts | Target Bridgehampton | 87323 | Signed SO/Pending Drawings | Yes | 2025-09-15 | 14004 | 8365.8 | Yes | No | Canceled Jobs | No | Remove - canceled on PM board | 2026-06-09 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/10053332448
Efrain Zarate | Jacobs Entertainment Inc | Jacobs Car Exhibit | 89857/2780 | Signed SO/Pending Drawings | Yes | 2026-10-01 | 300753.77 | 267498.82 | No | No | Not on PM board | No | Won in October (after 10/1 snapshot) | 2026-10-01 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/11546414255
Efrain Zarate | DC Petersen | 7 Brandermill | 92398 / 4479 | Signed SO/Pending Drawings | Yes | 2026-10-01 | 28415.78 | 25664.04 | No | No | Not on PM board | No | Won in October (after 10/1 snapshot) | 2026-10-01 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12858598587
Efrain Zarate | Architectural Windows & Doors | 68th Residence | 95408 | Signed SO/Pending Drawings | Yes | 2026-10-01 | 14484.42 | 12045.45 | No | No | Not on PM board | No | Won in October (after 10/1 snapshot) | 2026-10-01 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/13119424180
Efrain Zarate | Universal Windows Direct Las Vegas | L. Turner | 95407 | Signed SO/Pending Drawings | Yes | 2026-10-01 | 5718.75 | 5016.89 | No | No | Not on PM board | No | Won in October (after 10/1 snapshot) | 2026-10-01 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12972990773
Trevor Benthagen | Michael Graham, American First Builders | 94th and Bell Clubhouse | 91584 / 3047 | Signed SO/Pending Drawings | Yes | 2026-10-01 | 292413.88 | 262269.61 | No | No | Not on PM board | No | Won in October (after 10/1 snapshot) | 2026-10-01 | https://panda-windows-and-doors.monday.com/boards/7469134152/pulses/12407530626
Total