## Stages at 9-30
Sep Tab Row | Customer | Q Number | Deposit at 9/30 | Sept Result | Stage on file (Jul 31 link) | PM Board - Group | PM Board - Status | PM Board - On Hold Reason | Job to Floor | Production Completed | Final Invoice Requested | Shop Board - Group | Shop Board - Status | Shop Board - Production Status | Shop Board - Status Panda 3 | Shop Board - In Queue For | Shop Board - Date Completed | PM Last Updated | YOUR CODE (fill in)
2 | 1st Choice Glass:MUSC - Clemson | 88562 | 51110.14 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-08-19 |  |  | 4 Weeks Out | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-08-28
3 | 8G Solutions:Marina Square | 83756 | 14979.06 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
4 | AAC Glass Inc.:PUSD Folding Door | 88164 | 22283 | Open at 9/30 | Pre-Production | Pending Deposit in Invoicing | Pending Deposit |  |  |  |  | Not on Shop board | [5 empty] | 2026-09-21
5 | Aaron K. Martinez:Martinez Pivot | 92314 | 14518.74 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
6 | Advanced Windows:1990 K Street | 87616 | 35586 | Open at 9/30 | Pre-Production | Sent to Engineering | Sent to Engineering |  |  |  |  | Not on Shop board | [5 empty] | 2026-07-21
7 | AFR Construction:107 Augusta Pl | 89725 | 0 | Invoiced in Sept | 2026-09-16 | Waiting For Final to be Collected | Final Invoicing |  | 2026-08-05 |  | 2026-09-16 | Completed | Completed | Received at P3 | In Queue for Thermal | To update | 2026-09-18 | 2026-09-22
8 | Akis Doganis:Doganis Residence | 87185 | 31515 | Open at 9/30 | Pre-Production | Sent to Engineering | Sent to Engineering |  |  |  |  | Not on Shop board | [5 empty] | 2026-07-21
9 | Akis Doganis:Doganis Residence - Add on | 91559 | 50000 | Open at 9/30 | Pre-Production | Test Wall | Test Wall |  | 2026-08-25 |  |  | 1 Week Out | In Production | Received at P3 | In Queue for Thermal | To update |  | 2026-09-30
10 | American Eagle Glass, LLC:AAA Blue Diamond | 91452 | 8633.79 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
11 | American First Builders:Haven Lot #25 | 91539 | 110050.59 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-09-03 |  |  | 4 Weeks Out | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-09-29
12 | Architectural Glass & Design:9825 Stonecrest | 88159 | 12910 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-09-02 |  |  | Sent to Vendor | In Production | Received at P3 | In Queue for Thermal | To update |  | 2026-09-02
13 | Architectural Windows & Doors - AZ:Schulte Project | 91313 | 11021 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-08-28 |  |  | 1 Week Out | In Production | Received at P3 | In Queue for Thermal | To update |  | 2026-09-30
14 | Architectural Windows & Doors:NM Remodel | 91603 | 29226 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
15 | Arizona Glass Specialists:Greasewood Springs Community School | 90366 | 20063.72 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-09-17 |  |  | In Production | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-09-16
16 | AS Designs:39 Melanie Lane | 92233 | 218664 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
17 | Atlantic Window & Door:St Street Brooklyn | 92290 | 4398.38 | Open at 9/30 | Pre-Production | PM Review Documents | Avi Approval |  |  |  |  | Not on Shop board | [5 empty] | 2026-10-01
18 | Automatic Door & Glass:633 St. Croix Add On | 89869 | 0 | Invoiced in Sept | 2026-09-21 | Ready To Schedule Shipping/Pick Up | Schedule Pick Up |  | 2026-08-18 | 2026-09-30 | 2026-09-21 | Completed | Completed | Received at P3 | In Queue for Thermal | To update | 2026-09-30 | 2026-09-30
19 | AVI Windows & Doors:McCorkle | 91096 | 88551.09 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-09-28 |  |  | 4 Weeks Out | In Production | Received at P3 | In Queue for Thermal | To update |  | 2026-09-29
20 | Best Contracting LLC:UCSB San Benito Housing | 87022 | 60823 | Open at 9/30 | Pre-Production | Sent to Engineering | Sent to Engineering |  |  |  |  | Not on Shop board | [5 empty] | 2026-07-21
21 | Best Window Co.:Simms Residence | 89319 | 77139.86 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-08-07 |  |  | 5 Week Out | In Production | Received at P3 | In Queue for Thermal | To update |  | 2026-08-07
22 | BMG Door & Glass:Brown Window | 88405 | 0 | Invoiced in Sept | 2026-09-17 | Waiting For Final to be Collected | Final Invoicing |  | 2026-08-18 |  | 2026-09-17 | Completed | Completed | Received at P3 | In Queue for Thermal | To update | 2026-09-30 | 2026-09-30
23 | BMG Door & Glass:Halise Diamond | 89197 | 19024 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
24 | Brandon's Handyman Services:Kathy Wilson Windows v4 | 92249 | 4709.72 | Open at 9/30 | Pre-Production | Waiting For Final to be Collected | Final Invoicing |  | 2026-09-14 | 2026-10-01 | 2026-10-01 | Completed | Completed | Received at P3 | In Queue for Thermal | To update | 2026-10-02 | 2026-10-02
25 | Builders Direct Supply:4545 North-Studio | 85791 | 0 | Invoiced in Sept | 2026-09-09 | Awaiting Signed BOL/Pick Up Ticket/ Close Out | Awaiting Signed BOL |  | 2026-07-03 | 2026-09-09 | 2026-09-09 | Completed | Completed | Received at P3 | In Queue for Thermal | To update | 2026-09-09 | 2026-09-18
26 | Builders Direct Supply:Christian Rooney | 89792 | 34278 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-09-04 |  |  | 2 Weeks Out | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-10-01
27 | Builders Direct Supply:Johnson Entry Door | 91561 | 10289.43 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
28 | Builders Direct Supply:North 4545 | 83690 | 200341.5 | Open at 9/30 | Cutting | In Production | In Production |  | 2026-07-03 |  |  | 3 Weeks Out | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-09-30
29 | Builders FirstSource/Dixieline Lumber & Home Center:1416 Stone Canyon Rd | 89873 | 165000 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-07-13 |  |  | In Production | In Production | To Update | In Queue for Thermal | To update |  | 2026-09-24
30 | Builders FirstSource/Dixieline Lumber & Home Center:Kyle Newport | 90207 | 0 | Invoiced in Sept | 2026-09-03 | Completed - Closed Out | Completed - Closed Out |  | 2026-07-22 | 2026-09-04 | 2026-09-03 | Completed | Completed | Received at P3 | In Queue for Thermal | To update | 2026-09-04 | 2026-09-23
31 | C Thru Glass:Mt. Charleston Lodge | 89607 | 19335 | Open at 9/30 | Pre-Production | Sent to Engineering | Sent to Engineering |  |  |  |  | Not on Shop board | [5 empty] | 2026-07-21
32 | Cadowin, Inc:Simonson | 87583 | 16972.8 | Open at 9/30 | Pre-Production | PM Review Documents | PM Review |  |  |  |  | Not on Shop board | [5 empty] | 2026-09-29
33 | Capitol Glass Company:34th and San Pablo | 86644 | 17211.11 | Open at 9/30 | Pre-Production | Sent to Engineering | Sent to Engineering |  |  |  |  | Not on Shop board | [5 empty] | 2026-08-19
34 | Capitol Glass Company:The Eliza | 84966 | 39804 | Open at 9/30 | Pre-Production | Sent to Engineering | Sent to Engineering |  |  |  |  | Not on Shop board | [5 empty] | 2026-07-21
35 | Catalyst Acoustics Group | Unknown | 4108 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
36 | Charlotte Glass:Bridgeway Station West Building | 89234 | 16397.27 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-09-23 |  |  | 5 Week Out | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-09-23
37 | Christina Smith:Smith Residence | 91153 | 0 | Invoiced in Sept | 2026-09-08 | Completed - Closed Out | Completed - Closed Out |  | 2026-07-29 | 2026-09-08 | 2026-09-04 | Completed | Completed | Received at P3 | In Queue for Thermal | To update | 2026-09-08 | 2026-09-23
38 | CK2 Contracting:1221 W. Washington | 88868 | 0 | Invoiced in Sept | 2026-09-08 | Waiting For Final to be Collected | Final Invoicing |  | 2026-06-08 | 2026-09-08 | 2026-09-04 | Completed | Completed | Received at P3 | In Queue for Thermal | To update | 2026-09-08 | 2026-09-09
39 | Classic Glass:Hotel Mohi | 88845 | 51819 | Open at 9/30 | Pre-Production | Sent to Engineering | Sent to Engineering |  |  |  |  | Not on Shop board | [5 empty] | 2026-07-21
40 | Clear Custom:Newport Radius | 87745 | 26051.25 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-09-02 |  |  | Sent to Vendor | In Production | Received at P3 | In Queue for Thermal | To update |  | 2026-09-02
41 | Clerestory LLC:Malireddy Pivot Door | 89254 | 8136 | Open at 9/30 | Pre-Production | Sent to Engineering | Sent to Engineering |  |  |  |  | Not on Shop board | [5 empty] | 2026-09-22
42 | Colorado Building Supply:Mayberry Ranch | 90820 | 5841.5 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-09-01 |  |  | 2 Weeks Out | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-09-29
43 | Crystal Glass Inc.:New Logan Elementry | 83108 | 172204.5 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-08-11 |  |  | 4 Weeks Out | Crating | To Update | In Queue for Thermal | To update |  | 2026-09-17
44 | Dan and Molly Dirscherl:Dirscherl Cabana | 85777 | 17769 | Open at 9/30 | Pre-Production | Sent to Engineering | Sent to Engineering |  |  |  |  | Not on Shop board | [5 empty] | 2026-09-22
45 | Dan Gudov:Gudov Pivot | 92310 | 13512.99 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-09-29 |  |  | In Production | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-09-29
46 | David Valvida:Valdivia Residence | 91224 | 37539 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-09-11 |  |  | 3 Weeks Out | Crating | To Update | In Queue for Thermal | To update |  | 2026-09-30
47 | Desert Window Systems:Agave Ridge Lot 53 | 90986 | 13364.81 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-08-24 |  |  | Jobs on Hold | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-09-28
48 | Desert Window Systems:Agave Ridge Lot 54 | 91574 | 17427.78 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-08-24 |  |  | Late | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-09-28
49 | Desert Window Systems:Lennar 2 | 90600 | 0 | Invoiced in Sept | Assembly | Crating | Packaging/Crating |  | 2026-06-16 |  | 2026-09-28 | Jobs on Hold | In Production | Received at P3 | In Queue for Thermal | To update |  | 2026-09-28
50 | Donatello Bonasera Development, LLC:Casa Faten | 88756 | 160000 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-08-06 |  |  | Sent to Vendor | In Production | Received at P3 | In Queue for Thermal | To update |  | 2026-09-22
51 | Don's Mobile Glass:Michael Raimondo | 90442 | 0 | Invoiced in Sept | 2026-09-14 | Completed - Closed Out | Completed - Closed Out |  | 2026-07-29 | 2026-09-15 | 2026-09-15 | Completed | Completed | Received at P3 | In Queue for Thermal | To update | 2026-09-15 | 2026-09-23
52 | Dugally Oberfeld, Inc.:Cox | 83729 | 31223 | Open at 9/30 | Assembly | In Production | In Production |  | 2026-05-14 |  |  | Jobs on Hold | In Production | Received at P3 | In Queue for Thermal | To update |  | 2026-09-22
53 | Dynamic Glass:Antero Resources | 85504 | 151068 | Open at 9/30 | Pre-Production | Sent to Engineering | Sent to Engineering |  |  |  |  | Not on Shop board | [5 empty] | 2026-07-21
54 | E & Z Glass & Window:Sparrow Partners | 87546 | 0 | Invoiced in Sept | Pre-Production | Crating | Packaging/Crating |  | 2026-09-08 | 2026-10-01 | 2026-09-30 | Completed | Completed | Received at P3 | In Queue for Thermal | To update | 2026-10-01 | 2026-10-01
55 | E & Z Glass & Window:Tollway Office Building | 90853 | 0 | Invoiced in Sept | 2026-09-21 | Awaiting Signed BOL/Pick Up Ticket/ Close Out | Awaiting Signed BOL |  | 2026-06-29 | 2026-09-18 | 2026-09-21 | Completed | Completed | Received at P3 | In Queue for Thermal | To update | 2026-09-18 | 2026-09-30
56 | Echelon Builders LLC:Residential | 89324 | 0 | Invoiced in Sept | 2026-09-21 | Ready To Schedule Shipping/Pick Up | Schedule Shipping |  | 2026-06-24 | 2026-09-21 | 2026-09-21 | Completed | Completed | Received at P3 | In Queue for Thermal | To update | 2026-09-21 | 2026-09-30
57 | Element Facades 13:299 MILWAUKEE | 86960 | 17924 | Open at 9/30 | Coating | In Production | In Production |  | 2026-07-22 |  |  | 2 Weeks Out | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-09-28
58 | Elevate Home:4005 Alonzo Ave | 91449 | 7224.09 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
59 | Elham Taherian:2180 Havensight Add On 2 | 91377 | 7479.09 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
60 | Elite Glazing Group:LA Basketball | 90706 | 30536 | Open at 9/30 | Pre-Production | Sent to Engineering | Sent to Engineering |  |  |  |  | Not on Shop board | [5 empty] | 2026-07-21
61 | Elite Glazing Inc.:RSF Clubhouse | 85987 | 0 | Invoiced in Sept | 2026-09-25 | Crating | Packaging/Crating |  | 2026-06-04 |  | 2026-09-25 | Late | Test Wall | Received at P3 | In Queue for Thermal | To update |  | 2026-10-01
62 | ELMNTL:S2 | 89863 | 48111.93 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-08-13 |  |  | Late | Crating | To Update | In Queue for Thermal | To update |  | 2026-09-30
63 | Environmental Glass Inc:Ann Arbor Thurston | 84161 | 176687 | Open at 9/30 | Pre-Production | Sent to Engineering | Sent to Engineering |  |  |  |  | Not on Shop board | [5 empty] | 2026-07-21
64 | Environmental Glass Inc:Mitchell Elementary | 81492-R1 | 114974 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-09-11 |  |  | Sent to Vendor | In Production | Received at P3 | In Queue for Thermal | To update |  | 2026-09-10
65 | Epsilon Windows & Doors:Peggie Brown | 91450 | 0 | Invoiced in Sept | 2026-09-23 | Waiting For Final to be Collected | Final Invoicing |  | 2026-08-19 |  | 2026-09-22 | Completed | Completed | Received at P3 | In Queue for Thermal | To update | 2026-09-28 | 2026-09-28
66 | FAS Exteriors:Shaughnessy Res 216034 | 90324 | 11312 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-08-20 |  |  | 1 Week Out | In Production | Received at P3 | In Queue for Thermal | To update |  | 2026-09-28
67 | Ford Metro Inc:Chapter / Ann Arbor | 87492 | 22079 | Open at 9/30 | Pre-Production | Sent to Engineering | Sent to Engineering |  |  |  |  | Not on Shop board | [5 empty] | 2026-07-21
68 | Four Corners Building Supply:Bonaire Park - Building A | 91704 | 43056 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-09-28 |  |  | In Production | In Production | Received at P3 | In Queue for Thermal | To update |  | 2026-09-28
69 | Garry and Angie Tomashowski:Tomashowski | 92257 | 45000 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-09-21 |  |  | 5 Week Out | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-09-21
70 | Giroux Glass:SoCalGas Loggia | 88082 | 0 | Invoiced in Sept | 2026-09-16 | Awaiting Signed BOL/Pick Up Ticket/ Close Out | Awaiting Signed BOL |  | 2026-07-01 | 2026-09-30 | 2026-09-16 | Completed | Completed | Received at P3 | In Queue for Thermal | To update | 2026-09-30 | 2026-10-01
71 | Giroux Glass:Sparks Training Facility | 89539 | 32606 | Open at 9/30 | Pre-Production | Pending Deposit in Invoicing | Pending Deposit |  |  |  |  | Not on Shop board | [5 empty] | 2026-07-21
72 | Glass and Metals, Inc:2100 Crystal | 88012 | 25461 | Open at 9/30 | Pre-Production | Pending Deposit in Invoicing | Pending Deposit |  |  |  |  | Not on Shop board | [5 empty] | 2026-09-22
73 | Glass House LLC:Red Arrow | 88675 | 0 | Invoiced in Sept | Canceled 9/4/2026 | Not on PM board | [5 empty] | Not on Shop board
74 | Glass House Products:Lawther - add on | 91743 | 0 | Invoiced in Sept | 2026-09-15 | Completed - Closed Out | Completed - Closed Out |  |  | 2026-09-13 | 2026-09-15 | Completed | Completed | Received at P3 | In Queue for Thermal | To update | 2026-09-13 | 2026-09-23
75 | Glass House Products:Lawther Remodel | 90930 | 0 | Invoiced in Sept | 2026-09-15 | Completed - Closed Out | Completed - Closed Out |  |  | 2026-09-13 | 2026-09-15 | Completed | Completed | Received at P3 | In Queue for Thermal | To update | 2026-09-13 | 2026-09-23
76 | Goldfinch Brothers:Stoel Rives L48 | 89287 | 0 | Invoiced in Sept | 2026-09-09 | Canceled Jobs | Canceled |  |  |  |  | Not on Shop board | [5 empty] | 2026-09-24
77 | Grand View Glass:LMAC Operable Glass Wall | 89541 | 9278.28 | Open at 9/30 | Pre-Production | Pending Deposit in Invoicing | Pending Deposit |  |  |  |  | Not on Shop board | [5 empty] | 2026-07-21
78 | Hardman Glazing Management LLC:800 Corte Madera | 89412 | 20897 | Open at 9/30 | Coating | In Production | In Production |  | 2026-06-18 |  |  | Sent to Vendor | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-09-22
79 | Hardman Glazing Management LLC:Utility building - 800 Corte Madera | 89867 | 14271.62 | Open at 9/30 | Coating | In Production | In Production |  | 2026-06-19 |  |  | Sent to Vendor | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-09-11
80 | HBS Inc.:Burns | 87391 | 60000 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-08-18 |  |  | Jobs on Hold | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-09-25
81 | Heart of America Aston LLC:592 Aston | 84210 | 31567 | Open at 9/30 | Coating | In Production | In Production |  | 2026-05-22 |  |  | Sent to Vendor | In Production | To Update | In Queue for Thermal | To update |  | 2026-09-28
82 | Integrated Glass Concepts, Inc:Diablo Valley College | 87488 | 0 | Invoiced in Sept | 2026-09-23 | Waiting For Final to be Collected | Final Invoicing |  | 2026-06-22 | 2026-09-23 | 2026-09-22 | Completed | Completed | Received at P3 | In Queue for Thermal | To update | 2026-09-23 | 2026-09-24
83 | Island Tiles:Hilton Ballroom Doors | 89316 | 0 | Invoiced in Sept | 2026-09-25 | Waiting For Final to be Collected | Final Invoicing |  | 2026-06-01 | 2026-09-25 | 2026-09-25 | Completed | Completed | Received at P3 | In Queue for Thermal | To update | 2026-09-25 | 2026-10-01
84 | J Shuman Door Installation:Hospitality Building | 86579 | 69123 | Open at 9/30 | Pre-Production | Sent to Engineering | Sent to Engineering |  |  |  |  | Not on Shop board | [5 empty] | 2026-07-01
85 | J Shuman Door Installation:Nandini Saraiya | 89168 | 30691 | Open at 9/30 | Pre-Production | Sent to Engineering | Sent to Engineering |  |  |  |  | Not on Shop board | [5 empty] | 2026-07-21
86 | JDM Contractors:JSSK | 92326 | 47956.69 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-09-15 |  |  | Expedite! | In Production | Received at P3 | In Queue for Thermal | To update |  | 2026-09-25
87 | Jeff Crook:16 A Solitude | 91192 | 36332.46 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-09-14 |  |  | 3 Weeks Out | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-10-02
88 | Jeff Kohler:Living Room | 89722 | 3826 | Open at 9/30 | Pre-Production | PM Review Documents | PM Review |  |  |  |  | In Production | In Production | To Update | In Queue for Thermal | To update |  | 2026-10-01
89 | Jeremy D. Whalon:Whaleon Residence | 86092 | 9201 | Open at 9/30 | Pre-Production | Sent to Engineering | Sent to Engineering |  |  |  |  | Not on Shop board | [5 empty] | 2026-09-22
90 | John Burke:Burke Pivot | 91288 | 0 | Invoiced in Sept | 2026-09-04 | Ready To Schedule Shipping/Pick Up | Schedule Shipping |  |  | 2026-09-03 | 2026-09-04 | Completed | Completed | Received at P3 | In Queue for Thermal | To update | 2026-09-03 | 2026-09-22
91 | KCR Development:Rec Pav 2 | 88266 | 40071 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-09-02 |  |  | Sent to Vendor | In Production | Received at P3 | In Queue for Thermal | To update |  | 2026-09-02
92 | Keith Starkey:Starkey Residence | 78503 | 15815 | Open at 9/30 | Pre-Production | Sent to Engineering | Sent to Engineering |  |  |  |  | Not on Shop board | [5 empty] | 2026-07-21
93 | Kell-Chuck Glass Company:Drew Phillips | 90719 | 7000 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-09-17 |  |  | 4 Weeks Out | In Production | To Update | In Queue for Thermal | To update |  | 2026-09-17
94 | Kelly Maiello Architects:Large Conference Room Job | 90032 | 9955 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-08-18 |  |  | Late | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-10-02
95 | Ken Caryl Glass:Marcus Meyer | 90364 | 11314.88 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-08-24 |  |  | 1 Week Out | In Production | Received at P3 | In Queue for Thermal | To update |  | 2026-09-29
96 | Keystone Distribution:The Martin | 88971 | 18595.53 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
97 | Klein-Dickert Milwaukee, Inc.:Artalia Senior Living | 90043 | 10982.91 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
98 | Kumara Valla:Valla Doors | 88804 | 19363.69 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-09-18 |  |  | 5 Week Out | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-09-18
99 | Lakewood Glass & Screen:Cohen Residence | 91310 | 57000 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-09-11 |  |  | Sent to Vendor | In Production | Received at P3 | In Queue for Thermal | To update |  | 2026-09-14
100 | Lee Glass and Window:Eisenhower Elementary School Expansion | 90333 | 8649.91 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
101 | Liberty Glass & Metal Inc:Irvine | 89690 | 13551.62 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
102 | Lighthouse Windows, Inc.:Warm Springs III - Lot 10 | 91004 | 13225.66 | Open at 9/30 | Pre-Production | Pending Deposit in Invoicing | Pending Deposit |  |  |  |  | Not on Shop board | [5 empty] | 2026-07-21
103 | Linares Construction LLC:Spears Residence | 91495 | 12762.73 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-09-01 |  |  | 2 Weeks Out | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-09-30
104 | Lincoln Glass & Mirror:Concord | 89522 | 8200 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
105 | Lite Building Services:1420 King Street 6th Floor Ribbon Window | 85604 | 80676.28 | Open at 9/30 | Assembly | In Production | In Production |  | 2026-05-14 |  |  | Jobs on Hold | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-09-02
106 | Mark Industries LTD:Worth SD P27 | 80858 | 6843 | Open at 9/30 | Pre-Production | Sent to Engineering | Sent to Engineering |  |  |  |  | Not on Shop board | [5 empty] | 2026-06-18
107 | Maryl Construction:91108 Hapuna Villa Window | 91108 | 5016.61 | Open at 9/30 | Pre-Production | Pending Deposit in Invoicing | Pending Deposit |  |  |  |  | Not on Shop board | [5 empty] | 2026-07-21
108 | Maxwell Construction:Kane County Office of Tourism | 90183 | 18889 | Open at 9/30 | Coating | In Production | Receive Signed Drawings |  | 2026-06-11 |  |  | Sent to Vendor | In Production | Received at P3 | In Queue for Thermal | To update |  | 2026-09-03
109 | Mazzarino Construction & Development, LTD:Mazzarino Residence | 90746 | 13469.26 | Open at 9/30 | Cutting | In Production | In Production |  | 2026-07-22 |  |  | Jobs on Hold | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-09-14
110 | McInerney & Associates:Au Chavel | 90089 | 36368.01 | Open at 9/30 | Cutting | Crating | Packaging/Crating |  | 2026-07-22 | 2026-09-30 |  | Late | Packaging | Received at P3 | In Queue for Thermal | To update | 2026-09-30 | 2026-10-01
111 | Mesa Properties:2435 Legacy Dr | 85687 | 13294 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
112 | Mexican Bar Co.:Mexican Bar Company | 88593 | 70606.89 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-09-02 |  |  | 4 Weeks Out | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-09-02
113 | Michael Summers:8214 Dutch Harbor | 91695 | 0 | Invoiced in Sept | 2026-09-23 | Completed - Closed Out | Completed - Closed Out |  | 2026-08-28 | 2026-09-29 | 2026-09-23 | Completed | Completed | Received at P3 | In Queue for Thermal | To update | 2026-09-29 | 2026-10-01
114 | Mike Opitz:Opitz Residence | 89558 | 0 | Invoiced in Sept | 2026-09-15 | Awaiting Signed BOL/Pick Up Ticket/ Close Out | Awaiting Signed BOL |  | 2026-08-13 | 2026-09-25 | 2026-09-15 | Completed | Completed | To Update | In Queue for Thermal | To update | 2026-10-02 | 2026-10-02
115 | MSW Glass Inc. d.b.a Skyline Glass Inc:Candela's Apartments | 86208 | 22287 | Open at 9/30 | Pre-Production | Sent to Engineering | Sent to Engineering |  |  |  |  | Not on Shop board | [5 empty] | 2026-07-21
116 | Newton Construction:1865 Woodhaven | 89295 | 26512 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-08-25 |  |  | 8 Weeks Out | In Production | Received at P3 | In Queue for Thermal | To update |  | 2026-09-23
117 | Newton Construction:Delarosa | 91457 | 14380 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-09-23 |  |  | 4 Weeks Out | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-09-22
118 | OC PATIO DOORS:Victoria's Casement | 92060 | 3607.38 | Open at 9/30 | Pre-Production | PM Review Documents | PM Review |  |  |  |  | Not on Shop board | [5 empty] | 2026-10-02
119 | Pacific Glazing Contractors:Netflix Bldg G - Pacific | 88850 | 49392 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-08-14 |  |  | Sent to Vendor | In Production | Received at P3 | In Queue for Thermal | To update |  | 2026-10-01
120 | Patrick Krejcik:Krejcik Project | 89066 | 0 | Invoiced in Sept | 2026-09-14 | Completed - Closed Out | Completed - Closed Out |  | 2026-07-30 | 2026-09-17 | 2026-09-11 | Completed | Completed | Received at P3 | In Queue for Thermal | To update | 2026-09-17 | 2026-09-23
121 | Peak Glass Inc.:555 Scott Lane | 90778 | 7737.76 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
122 | Pella OKC:Hoffman-Lenox | 85309 | 14942 | Open at 9/30 | Coating | Need to Request Final Invoice | Request Final Invoice |  | 2026-06-16 | 2026-10-01 | 2026-10-01 | Completed | Completed | Received at P3 | In Queue for Thermal | To update | 2026-10-01 | 2026-10-01
123 | Pella OKC:Pella Bi-Fold | 87536 | 17907.14 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-08-13 |  |  | 5 Week Out | In Production | To Update | In Queue for Thermal | To update |  | 2026-10-01
124 | Platinum Glass LLC:Phase 3 Library Door | 90985 | 26358 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-08-24 |  |  | Sent to Vendor | In Production | Received at P3 | In Queue for Thermal | To update |  | 2026-08-27
125 | Polk Architectural:247 Mesa Dr | 91342 | 8404.57 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-09-14 |  |  | 4 Weeks Out | In Production | To Update | In Queue for Thermal | To update |  | 2026-09-22
126 | Polk Architectural:Randy Rodgers | 91029 | 13195.06 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-08-28 |  |  | 1 Week Out | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-09-30
127 | Portland Millwork:Reser Residence | 89071 | 44750.18 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-08-03 |  |  | 1 Week Out | In Production | Received at P3 | In Queue for Thermal | To update |  | 2026-09-30
128 | Precision Glass Co.:235 Oak - 2 | 91555 | 0 | Invoiced in Sept | 2026-09-08 | Completed - Closed Out | Completed - Closed Out |  | 2026-07-23 | 2026-09-08 | 2026-09-04 | Completed | Completed | Received at P3 | In Queue for Thermal | To update | 2026-09-08 | 2026-09-23
129 | Proper Construction:Mayorga Residence | 90614 | 0 | Invoiced in Sept | 2026-09-01 | Completed - Closed Out | Completed - Closed Out |  | 2026-07-13 | 2026-09-01 | 2026-09-01 | Service |  | Received at P3 | In Queue for Thermal | To update |  | 2026-09-23
130 | Redhawk Glass Inc:Granton Casino | 90916 | 0 | Open at 9/30 | 2026-09-10 | Completed - Closed Out | Completed - Closed Out |  | 2026-07-30 | 2026-09-08 | 2026-09-04 | Completed | Completed | Received at P3 | In Queue for Thermal | To update | 2026-09-08 | 2026-09-23
131 | Reflection Window & Wall:Bally's Chicago Casino | 90293 | 17650.97 | Open at 9/30 | Pre-Production | Sent to Engineering | Sent to Engineering |  |  |  |  | Not on Shop board | [5 empty] | 2026-09-22
132 | Rick Roberson:Roberson | 92121 | 30970.43 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-08-25 |  |  | In Production | In Production | Received at P3 | In Queue for Thermal | To update |  | 2026-09-14
133 | RiverWoods Mill:Jeperson Remodel 4 PHASE 1 | 92246 | 10549.85 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
134 | RiverWoods Mill:Slade Quote | 90085 | 0 | Invoiced in Sept | 2026-09-17 | Completed - Closed Out | Completed - Closed Out |  | 2026-06-29 | 2026-09-16 | 2026-09-16 | Completed | Completed | Received at P3 | In Queue for Thermal | To update | 2026-09-16 | 2026-09-23
135 | RKB Custom Homes:1064 Willowbrook | 90766 | 32000 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-09-08 |  |  | In Production | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-09-04
136 | Royal Palm Aluminum, Inc.:399 Royal Palm Way | 88490 | 0 | Invoiced in Sept | Assembly | Test Wall | Test Wall |  | 2026-05-27 |  | 2026-09-30 | Late | Packaging | Received at P3 | In Queue for Thermal | To update |  | 2026-10-01
137 | Royal Waikiki LLC:5699 Kalanianaole Hwy (doors) | 87713 | 192821 | Open at 9/30 | Coating | In Production | In Production |  | 2026-05-26 |  |  | Late | In Production | Received at P3 | In Queue for Thermal | To update |  | 2026-09-21
138 | Royal Waikiki LLC:5699 Kalanianaole Hwy (windows) | 87716 | 94522 | Open at 9/30 | Coating | In Production | In Production |  | 2026-06-04 |  |  | Late | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-08-28
139 | Sanjay Narang:40782 Marino Court | 91599 | 0 | Invoiced in Sept | 2026-09-15 | Waiting For Final to be Collected | Final Invoicing |  | 2026-07-28 | 2026-09-08 | 2026-09-15 | Late | Completed | Received at P3 | In Queue for Thermal | To update | 2026-09-08 | 2026-09-16
140 | Sierra Pacific - AZ:Folding Doors | 90500-1 | 25293.6 | Open at 9/30 | Pull Material | In Production | In Production |  | 2026-07-30 |  |  | Late | In Production | Received at P3 | In Queue for Thermal | To update |  | 2026-10-02
141 | Sierra Pacific - CA:1161 Bay Laurel St - Steel | 88948 | 55860.75 | Open at 9/30 | Assembly | In Production | In Production |  | 2026-05-22 |  |  | Sent to Vendor | In Production | To Update | In Queue for Thermal | To update |  | 2026-09-28
142 | Sierra Pacific - CA:2115 Oaks Steel Door | 88063 | 11338.47 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-07-22 |  |  | Completed | Completed | Completed | In Queue for Thermal | To update |  | 2026-09-24
143 | Sierra Pacific - CA:Alonso entry | 91860 | 7545.76 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-08-28 |  |  | 1 Week Out | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-09-29
144 | Sierra Pacific - CA:Lackey Voyage Pivot Door | 90567 | 7336.69 | Open at 9/30 | Pre-Production | Awaiting Signed BOL/Pick Up Ticket/ Close Out | Awaiting Signed BOL |  | 2026-08-06 | 2026-09-22 | 2026-09-21 | Completed | Completed | Received at P3 | In Queue for Thermal | To update | 2026-09-22 | 2026-09-28
145 | Sierra Pacific - CA:LTS.31 Door | 91679 | 17700.54 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-09-01 |  |  | In Production | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-09-24
146 | Sierra Pacific - CA:PO- 569-1530 A-Frame Builders | 92250 | 3937.6 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-09-30 |  |  | In Production | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-09-29
147 | Sierra Pacific - CA:PO-56901526 Dyer Construction | 91869 | 0 | Invoiced in Sept | Pre-Production | Waiting For Final to be Collected | Final Invoicing |  | 2026-08-18 |  | 2026-09-30 | Completed | Completed | Received at P3 | In Queue for Thermal | To update | 2026-10-02 | 2026-10-02
148 | Sierra Pacific Windows - WA:Wayside Pool House | 86062 | 0 | Invoiced in Sept | 2026-09-15 | Awaiting Signed BOL/Pick Up Ticket/ Close Out | Awaiting Signed BOL |  | 2026-08-12 | 2026-09-24 | 2026-09-15 | Completed | Completed | Received at P3 | In Queue for Thermal | To update | 2026-09-24 | 2026-09-30
149 | Sierra Pacific Windows:Williams Residence | 86334 | 5093.55 | Open at 9/30 | Pre-Production | Sent to Engineering | Sent to Engineering |  |  |  |  | Not on Shop board | [5 empty] | 2026-07-21
150 | Sightlines Glass:Blue Martini | 87599 | 51424.45 | Open at 9/30 | Pre-Production | Pending Deposit in Invoicing | Pending Deposit |  |  |  |  | Not on Shop board | [5 empty] | 2026-07-21
151 | Signature Glass & Windows, Inc.:3001 ECR | 87059 | 25737 | Open at 9/30 | Pre-Production | Sent to Engineering | Sent to Engineering |  |  |  |  | Not on Shop board | [5 empty] | 2026-07-21
152 | Signature Glass & Windows, Inc.:525 N Capitol | 84075 | 0 | Invoiced in Sept | 2026-09-23 | Waiting For Final to be Collected | Final Invoicing |  | 2026-05-12 | 2026-09-23 | 2026-09-23 | Completed | Completed | Received at P3 | In Queue for Thermal | To update | 2026-09-23 | 2026-09-24
153 | Sinter Clad:Mountain View 2 | 84726 | 231351 | Open at 9/30 | Cutting | In Production | In Production |  | 2026-04-29 |  |  | Late | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-07-13
154 | Sinter Clad:Mountain View 1 | 84719 | 416603 | Open at 9/30 | Assembly | In Production | In Production |  | 2026-04-22 |  |  | Late | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-09-16
155 | Socal Glass Inc.:Pechanga Eagles Nest | 88512 | 33240 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-08-28 |  |  | Sent to Vendor | In Production | Received at P3 | In Queue for Thermal | To update |  | 2026-09-22
156 | Socal Glass Inc.:Racquet Club | 88206 | 0 | Invoiced in Sept | 2026-09-04 | Glazing | Glazing |  | 2026-06-09 |  |  | Late | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-09-18
157 | Southwest Glass:Australia Exhibit | 87176 | 9608 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-09-23 |  |  | In Production | In Production | Received at P3 | In Queue for Thermal | To update |  | 2026-09-23
158 | St George Windows, Doors & More LLC:Dunes 10 Doors | 91551 | 43790.56 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-09-10 |  |  | 4 Weeks Out | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-09-14
159 | Stratos Development Inc:Eclipse Reidence | 86157 | 255026 | Open at 9/30 | Pre-Production | Sent to Engineering | Sent to Engineering |  |  |  |  | Not on Shop board | [5 empty] | 2026-07-21
160 | Stratos Development Inc:Kanani Residence | 86089 | 416889.25 | Open at 9/30 | Pre-Production | Sent to Engineering | Sent to Engineering |  |  |  |  | Not on Shop board | [5 empty] | 2026-07-21
161 | Stroker:Stroker Residence | 91760 | 13000 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-09-25 |  |  | 6 Weeks Out | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-09-24
162 | Sunset Glazing:6th & Palm | 84176 | 39098.2 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
163 | Sunshine Glass, LLC:415 College Main | 87805 | 7292 | Open at 9/30 | Pre-Production | Sent to Engineering | Sent to Engineering |  |  |  |  | Not on Shop board | [5 empty] | 2026-07-21
164 | Sunstride Construction:Everwild Project | 90372 | 0 | Invoiced in Sept | 2026-09-23 | Completed - Closed Out | Completed - Closed Out |  | 2026-06-26 | 2026-09-17 | 2026-09-18 | Completed | Completed | Received at P3 | In Queue for Thermal | To update | 2026-09-17 | 2026-09-23
165 | The Window Store LLC:Black Spur Estate | 85860 | 68221 | Open at 9/30 | Pre-Production | Sent to Engineering | Sent to Engineering |  |  |  |  | Not on Shop board | [5 empty] | 2026-07-21
166 | Tier One Custom Windows:1715 Sunset Dr | 91560 | 0 | Invoiced in Sept | 2026-09-14 | Waiting For Final to be Collected | Final Invoicing |  | 2026-08-13 |  | 2026-09-14 | Completed | Completed | Received at P3 | In Queue for Thermal | To update | 2026-09-24 | 2026-09-25
167 | Tier One Custom Windows:French Door | 90548 | 4673.7 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-09-24 |  |  | 5 Week Out | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-09-24
168 | Tier One Custom Windows:Wood Door | 91258 | 8755.11 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-08-07 |  |  | 7 Weeks Out | Schedule Shipping | Received at P3 | In Queue for Thermal | To update |  | 2026-09-24
169 | Trendex Window & Door:1826 S Bayshore Lane | 88397 | 59154.25 | Open at 9/30 | Pre-Production | Sent to Engineering | Sent to Engineering |  |  |  |  | Not on Shop board | [5 empty] | 2026-09-22
170 | Tridel Construction:2769 Marnay Lane | 90359 | 6614 | Open at 9/30 | Pre-Production | Test Wall | Test Wall |  | 2026-09-04 |  | 2026-10-01 | 3 Weeks Out | Test Wall | Received at P3 | In Queue for Thermal | To update |  | 2026-10-01
171 | Tridel Construction:Players Canyon - Doors | 84246 | 17115 | Open at 9/30 | Pre-Production | Sent to Engineering | Sent to Engineering |  |  |  |  | Not on Shop board | [5 empty] | 2026-07-21
172 | Turkel Design:Turkel Systems:GAL Residence | 87450 | 9898 | Open at 9/30 | Pre-Production | Sent to Engineering | Sent to Engineering |  |  |  |  | Not on Shop board | [5 empty] | 2026-07-21
173 | Velocity Glazing Inc.:Carmen Del Mar School | 90031 | 0 | Invoiced in Sept | Coating | In Production | In Production |  | 2026-07-15 |  | 2026-09-29 | 2 Weeks Out | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-09-29
174 | Vision Enclosure Walls:DFW Terminal C | 86704 | 90025 | Open at 9/30 | Pre-Production | Sent to Engineering | Sent to Engineering |  |  |  |  | Not on Shop board | [5 empty] | 2026-07-21
175 | Walters & Wolf - CA:UCB Bancroft | 87035 | 48949 | Open at 9/30 | Pre-Production | Sent to Engineering | Sent to Engineering |  |  |  |  | Not on Shop board | [5 empty] | 2026-07-21
176 | Westline Windows:Fir Way | 91683 | 20825 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-08-18 |  |  | Jobs on Hold | In Production | Received at P3 | In Queue for Thermal | To update |  | 2026-09-29
177 | JDP Associates:AULT PROJECT | 89465 | 31000 | Open at 9/30 | Pre-Production | PM Review Documents | PM Review |  |  |  |  | Not on Shop board | [5 empty] | 2026-09-23
178 | Harmon Inc - MD:725 W 12th St | 87189 | 221827.85 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
179 | Integrity Design & Build, LLC:Hughes Residence | 82453 | 9644.07 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-09-14 |  |  | In Production | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-09-14
180 | Elaine Fitzpatrick:Fitzpatrick Garage | 90886 | 3386 | Open at 9/30 | Pre-Production | PM Review Documents | PM Review |  |  |  |  | Not on Shop board | [5 empty] | 2026-10-01
181 | Epic Design Group Inc.:Lake Residence | 91787 | 29319.06 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
182 | Tier One Custom Windows:21830 Briarcliff Dr | 91556 | 18997.1 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
183 | Ken Caryl Glass:McDonald Audi | 91176 | 17692.43 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
184 | Turkel Design:Turkel Systems:Robbins | 89724 | 52988.75 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
185 | J Shuman Door Installation:1420 University Ave | 91748 | 65804.86 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
186 | J Shuman Door Installation:1285 W Edmundson Ave | 91739 | 5991.14 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
187 | Walters & Wolf - CA:HRHC Podium | 87948 | 66134.47 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
188 | Aragon Construction, Inc.:216B - Replacement | 92404 | 16888.09 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
189 | Kirk Moore:41 Caminito Amore | 92605 | 4787.94 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-09-23 |  |  | 5 Week Out | In Production | Received at P3 | In Queue for Thermal | To update |  | 2026-09-23
190 | Hidden Ridge Construction:310 Cold Smoke | 92369 | 5610.71 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
191 | J Shuman Door Installation:1901 Gilman Ranch Rd | 92172 | 39815.96 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
192 | Wenatchee Glass:Henley -MS | 92068 | 7504.65 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-09-29 |  |  | In Production | In Production | Received at P3 | In Queue for Thermal | To update |  | 2026-09-29
193 | Progress Glass:Marin Art & Garden Center | 91229 | 49156.8 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
194 | JDP Associates:Aldo Residence Add On | 95238 | 15928.34 | Open at 9/30 | Pre-Production | In Production | In Production |  | 2026-09-28 |  |  | In Production | Crating | Received at P3 | In Queue for Thermal | To update |  | 2026-09-28
195 | Sierra Pacific - CA:Fir Mountain Garage Sauna | 92755 | 1832.09 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
196 | Daniels Glass, Inc:Detroit Pistons Locker Room | 95229 | 12665.05 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
197 | Sierra Pacific - CA:4545 Tremont Doors | 91699 | 68772.35 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
198 | Ajay Glass & Mirror Co., Inc.:Billiter South | 90513 | 14835.63 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
199 | Ajay Glass & Mirror Co., Inc.:Sayers Resident | 92799 | 25255.76 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
200 | Window Installation Specialists:SDCCD Student Housing | 95062 | 13039.83 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
201 | Sierra Pacific - CA:1850 White Oak Dr. Corner Unit (TS.XO) | 95208 | 14983.84 | Open at 9/30 | Pre-Production | Pending Deposit in Invoicing | Pending Deposit |  |  |  |  | Not on Shop board | [5 empty] | 2026-09-25
202 | Sierra Pacific - CA:1850 White Oak | 92463 | 68279.14 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
203 | Scanlon Construction:736 El Medio | 95111 | 153638.59 | Open at 9/30 | Pre-Production | Not on PM board | [5 empty] | Not on Shop board
204 | Sierra Pacific Windows-CO:Silence Residence | 92285 | 120579.13 | Open at 9/30 |  | Not on PM board | [5 empty] | Not on Shop board
Total

## Stage Combos
PM Board - Group | PM Board - Status | Shop Board - Production Status | # Projects | Deposits at 9/30 | YOUR CODE (fill in)
In Production | In Production | Received at P3 | 63 | 3015317.54
Sent to Engineering | Sent to Engineering |  | 31 | 1837379.13
Not on PM board |  |  | 40 | 1533930.77
In Production | In Production | To Update | 9 | 543594.89
Pending Deposit in Invoicing | Pending Deposit |  | 8 | 174278.84
Test Wall | Test Wall | Received at P3 | 2 | 56614
PM Review Documents | PM Review |  | 4 | 54966.18
Crating | Packaging/Crating | Received at P3 | 1 | 36368.01
In Production | Receive Signed Drawings | Received at P3 | 1 | 18889
Need to Request Final Invoice | Request Final Invoice | Received at P3 | 1 | 14942
In Production | In Production | Completed | 1 | 11338.47
Awaiting Signed BOL/Pick Up Ticket/ Close Out | Awaiting Signed BOL | Received at P3 | 1 | 7336.69
Waiting For Final to be Collected | Final Invoicing | Received at P3 | 1 | 4709.72
PM Review Documents | Avi Approval |  | 1 | 4398.38
PM Review Documents | PM Review | To Update | 1 | 3826
Completed - Closed Out | Completed - Closed Out | Received at P3 | 1 | 0
Total
Open projects only (deposit still held at 9/30). Source: monday Project Managers board + Shop Updates board, pulled 10/2/26; Stage on file = Sep tab Stage column before update (linked to "As of 073126.xlsx").